## new machines
[5 empty] | Target | Planned
Actual
Delay
[6 empty] | Done | [6 empty] | FY2026 | [25 empty] | FY2027 | [52 empty] | FY2028
[13 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2 | [13 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2
[13 empty] | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September
TH/ GER | Project |  | A/B/C | PM/Sale/ Project owner /Status | Project phase | Status | Value |  |  | PO | Planed Margine % | Actual Margine % | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | Comment
| 56060_A_SI_VI5X Formats: 3 FAT (3 days; F2,F3;F5=10min) / 4 ( 5 adjust charts) I&C 1x mech. Tech. 10x days; 1x el. tech. 5x days Traininig 1x tech. for start-up & Training 5x days SAT by 1 technician for 3 days. |  | A | Stefanie | Delivery | QG status | 574127.8 | 0 | 0 | PO | 33.98% | 34% | [6 empty] | QG1 | QG2 | [8 empty] | QG3 | [10 empty] | QG4 | [9 empty] | QG5 |  | IFd | IFs | IFd | IFd | IFd | FAT | [6 empty] | QG6 | I&C | I&C | SAT | [50 empty] | Bantao will go on CW38 for 18 days and one VPT el. technician will go for 5 days
|  |  |  | Lucian+Rodrigo / Saksit |  | Milestones | [11 empty] | e-mail / VPT aftersales support | S | Communication Chanel sheet |  | Delivery end of August 2026 ( CW36/2026 ) Installation / Commissioning after delivery SAT at the latest in CW 38/2026 |  | L,F,D |  |  |  |  | final format overview | BSRA | WTr=8700€ - 6% |  |  |  | WTr=8700€ - 6% |  |  | WTc | need to modify wear & tear parts list |  |  | carton transport parts pending (returned from QC) | TM,need to modify wear & tear parts list | IP; carton transport group 2518545, currently it is estimated to arrive beginning of next week (CW22). We are following this closely | WTr= 8700 - 6% = 8178 Euro (add the pricing which we get roughly 9,660 euro.) no need to stay 8178 Euro | WTr= 8700 - 6% = 8178 Euro (add the pricing which we get roughly 9,660 euro.) no need to stay 8178 Euro | TM (glue); arrived carton transport group 2518545 | WTc |  |  | IP | WTc | receive parts for new light curten was relesed 10.7. | receive parts for new light curten was relesed 10.7. | need to prictise manual loading (F3=F5) | BSRA(D) | pack with machine 3 samples that we run on machine during FAT |  | summery parts return to store | Operating manual into the Slovenian language (actual costs or the translation are exceeding the planned & sold costs for this item. As you can see below. i added 146,000 (4000 euro) to special costs ) | PM-A | flight delayed | Operating manual into the Slovenian language (actual costs or the translation are exceeding the planned & sold costs for this item. As you can see below. i added 146,000 (4000 euro) to special costs ) | Vivek approved visa on 23.9. when will come el.technician from VPT (Marino) on CW40 | warranty starts (warranty is 12 months or 2000 operation housr, depend on which occure firest. Warranty valid starting after SAT but not latter then 90 days after FAT) | We need to charge customer for travelling expense, and accommodations | BSRA(end) |  | PM e-mail Acounting, no more expenses on project
|  |  |  | 56061 Teerasak / Wichawut |  | Design | [12 empty] | Lp | Fp | B,O | [5 empty] | W,SO | W | SO; ND(top clooser, 68 stations,calculation for carton transport) | FP | FD (top clooser) Design confirmed no need |  |  |  |  | P | Power and Air supply details sheet with location on machine | [9 empty] | SW | [11 empty] | SAP format marking
[6 empty] | Operation | [46 empty] | set F4
|  |  |  | Planned | Delivery | Q (quality) | [12 empty] | QG1 | QG2 | [6 empty] | QG3 (I would like to request to postpone QG3 for 56061 Henkel VI5 from CW02 to CW05 (end of Jan). At the QG2, I have underestimate for design hour and design capacity of this project.) |  | QG3(with customer need to discuss manual loading concept) | [7 empty] | QG4 (basic not in house; many added parts) |  | QG4 (meny additional parts, seted priority part for CW15) | QG4(to follow on CW17 additionaly ordered parts for manual infeed area…we can pass on CW19) | [6 empty] | QG5 (on CW21 we moved QG5 from CW22 to CW24 due to carton transport pending) |  |  | QG5 (new light curten was relesed) |  | IFd(F2) | IFd(F3) | IFd(F3;F5) manual loading was slow | IFd(F3;F5) | IFd(F3;F5) | FAT | [5 empty] | I&C | QG6 | I&C | I&C | SAT
|  |  |  | Actual |  | C (cost) | [13 empty] | PEC |  |  | 34% | D,M |  |  |  |  | D,M | 34% |  |  | D,M,A,P | 34% |  | 36% | D,M,A,P |  |  |  |  | D,M,A,P | 34% |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P |  |  |  | D,M,A,P
|  |  |  | Actual |  | D (Delivery) | [12 empty] | FAT in CW32/2026 Delivery end of August 2026 ( CW36/2026 ) Installation / Commissioning after delivery SAT at the latest in CW 38/2026 | [39 empty] | P,L | P | ETD | L,ETD | P;L,ETD | ETA | [53 empty] | FOB Bangkok, AIR delivery; packing; loading; ETD 12.09. / ETA 16.09.
|  |  |  | Planned |  | Payment | 477303.4 |  |  | 4578710291 | [8 empty] | PO | i30% |  |  |  | p30% |  |  | p30% | [29 empty] | i30% | [8 empty] | i30% |  |  |  | p30% | [8 empty] | p30% |  |  |  | i10% | p10% | [33 empty] | (credit term 90 days) 30% (DP) 30% (after FAT); 30% (after successful SAT, however, no later than 45 days after installation if main acceptance tests shouldbe delayed for reasons for which Henkel is responsible). 10% after expiry of the warranty period or with the final invoice against bank guarantee S/O: 6080056060
| 56060_Henkel Maribor_SI_VI5X FAT in VPT |  |  | Add-on |  | Delivery (Add on) | 43750
|  |  |  | Done |  | Payment (Add on) | [15 empty] | Qto | [95 empty] | canceled
| 56060_Henkel Maribor_SI_VI5X delivery by AIR |  |  | Add-on |  | Delivery (Add on) | 90000 |  |  | 4578710291 | [107 empty] | DAP Maribor, AIR delivery
|  |  |  | Planned |  | Payment (Add on) | [15 empty] | Qto | [7 empty] | PO | i30% |  |  | i30% |  |  |  | p30% |  |  |  | p30% | [14 empty] | i30% | [8 empty] | i30% |  |  |  | p30% | [8 empty] | p30% |  |  |  | i10% | p10% | [33 empty] | 30% (DP) 30% (after FAT); 30% (after successful SAT, however, no later than 45 days after installation if main acceptance tests shouldbe delayed for reasons for which Henkel is responsible). 10% after expiry of the warranty period or with the final invoice against bank guarantee
| 56060_Henkel Maribor_SI_VI5X concept for new program for manual loading |  |  | Add-on |  | Delivery (Add on) | 4869.2 | [23 empty] | 2 options (continues mode, speed 30-50 (operator can miss); cartons stop at each position to allow product loading speed and OEE may be lower or unstable
|  |  |  | Planned |  | Payment (Add on) | [23 empty] | Qto | PO?
| 56060_Henkel Maribor_SI_VI5X additional emergancy; Manual infeed mode and Insertion Assistance Toolkits |  |  | Add-on |  | Delivery (Add on) | 6824.4 |  |  | 4579073062
|  |  |  | Planned |  | Payment (Add on) | [32 empty] | Qto | PO | [77 empty] | 30% (DP) 30% (after FAT); 30% (after successful SAT, however, no later than 45 days after installation if main acceptance tests shouldbe delayed for reasons for which Henkel is responsible). 10% after expiry of the warranty period or with the final invoice against bank guarantee
|  |  |  | Apichat |  | Milestones | [26 empty] | same as Propak 2025. Just only the P&P mechanism is same as Panasonic for easy convert to Panasonic 2nd machine. And the exhibition format is not yet defined. | Format to check with Apicaht, Wolfgan |  | F (confirmed to go with existing format for tuth brush) If we will go with 4 lines, we will need to glue 8 lines of top carts as plates are with 12 lines. | 3D to be prepared by Annop, Henoch after to update wiring. BSRA | this machine will be for Panasonic so we will keep as previous mechine I wanted to let you know that Teerawat has entered and released the bill of materials for the machine in CSPB. Now that we've made the decision to replace the Festo drives with ILM drives, it's important that we proceed with equipping this machine with ILM drives and ensure that both the CAD files and SAP records are updated accordingly. | Georg = Regarding testing material, we have also some quantity in stock, we will check how much we need and let you know additional quantity we need from you. |  |  |  | George sent about 4000 blisteds and hood |  |  | TM (from VPT) | on 29.5. from Konrad: received samples from the current Interpack application, which features 4 materials, to showcase the possibilities. The Interpack format will not be demonstrated live at the Propack or Allpack trade shows. |  |  | TM(Hood = 12,600; Top Card = 16,800; Brush=2600) | missing parts for format parts: GN 2662090 4216868 = 1 pc. GN 2662093 2701636 = 8 pcs. 7469 = 1 pc. GN 2662098 2700218 = 2 pcs. 2700219 = 2 pcs. 4301257 = 1 pc. GN 2662094 2700218 = 10 pcs. 2700219 = 10 pcs. GN 2662547 4203023 = 6 pcs.) | start with weeklyt meetings |  | FP (need to modify after visit from VPT for All pack exibition) | FP (need to modify after visit from VPT for All pack exibition) |  | complete assembly | complete assembly | must receive format parts | BSRA(D) | received all format parts | send testing material (Hood = 12,600; Top Card = 16,800; brush=2600) | summery parts return to store |  | BSRA(end) |  |  | AllPack exibition Indonesia 20-23.10.2026. | deal with Schiffer India? | [8 empty] | PM e-mail Acounting, no more expenses on project
|  |  |  | 56151 Teerawat / Jidpanu |  | Design | [29 empty] | O | FP (need to modify) | W | [5 empty] | FP (missing parts for format parts that I told you in meeting. I just ordered: GN 2662090 4216868 = 1 pc. GN 2662093 2701636 = 8 pcs. 7469 = 1 pc. GN 2662098 2700218 = 2 pcs. 2700219 = 2 pcs. 4301257 = 1 pc. GN 2662094 2700218 = 10 pcs. 2700219 = 10 pcs. GN 2662547 4203023 = 6 pcs.) |  |  |  |  | P |  |  |  |  | SW | FP(released new format parts) | FP(released new format parts) | SW | [5 empty] | SAP format marking
[6 empty] | Operation | [51 empty] | ECR | SO
|  |  |  | Planned | #REF! | Q (quality) | [27 empty] | QG2 |  | QG3 | [12 empty] | QG4 (besic and option not in house) |  | QG4 (many parts still missing, last part on CW28) |  | QG4 (option not in house) | QG4 (Lifting unit sealing 2662054 – linear guide 4214792 get end of CW31) |  | QG4 | QG5 |  | QG5 | QG5 | IFd | IFd
|  |  |  | Actual |  | C (cost) | [28 empty] | PEC |  | D |  |  |  |  | D,M |  |  |  | D,M |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P
|  |  |  | Actual |  | D (Delivery) | [56 empty] | P,L | ETD |  | ETA | [51 empty] | AllPack exibition packing 17.9.2026. Loading 17.9.2026. ETD: 22.09.2026; ETA: 26.09.2026
|  |  |  | Planned |  | Payment | [27 empty] | PO | [34 empty] | PO | [48 empty] | qw
| 56040_B_CN_SC5-CondomFeeder Formats: 4 FAT (12 days; 30min) / 4 (4 adjustment charts) I&C by 1 Thai & 1 Chinese service technician for 6 days Execution IQ/OQ by 2Thai & 1Chinese service technicians for 4 days Training by 2 Thai & 1 Chinese service technicians for 2 days |  | B | Karan | Setting phase | QG status | 1046999.5 | 0 | 0 | PO | 29.53% | 32% |  |  |  | QG2 | QG2 |  |  |  | QG3-3 |  | DR |  |  |  |  | QG3-1 |  | FR | QG4-3 | QG5-3 |  | TEST | QG4-1 |  | QG3-2 | [6 empty] | QG5-1 | QG4-2 | [5 empty] | QG5-2 | IFs |  | IFd | IFd | IFd | IFd |  |  |  |  | FAT | [5 empty] | QG6 |  |  | I&C | I&C | SAT | [44 empty] | QG3-1 = SC5; QG3-2 = condom feeders QG3-3 = first unit for test (condom feeder)
|  |  |  | Patinya / Saksit |  | Milestones | [10 empty] | Communication Chanel sheet | e-mail / VPT aftersales support | S, 3D inkjet and camera | L | F | S, 3D inkjet and camera | S, 3D inkjet and camera | F | TM(for first unit) |  |  | F | F |  |  |  |  | clarify all for ordering remaining 3 units +4 +4 = 11 units | IP | clarify all for ordering remaining 3 units +4 +4 = 11 units | receive from customer inkjet and camera | BSRA |  | DQ customer want to combine for both (Karan will arange meeting) |  |  | TM | TM (carton will arrive on CW19) | during QG4-2 on CW20 we need to discuss plan for assembly and test of one condom feeder unit | WTc | TM (carton ) | IP | TM(carton for last format) | liniar guide x 16 delivery on 17.6. | DQ customer want to combine for both | TM (condom) 29.6. | WTc |  | customer did not send inkjet and camera…will be instaled during SAT |  |  | IP | BSRA(D) | IP |  |  | IP | pack with machine 3 samples that we run on machine during FAT | summery parts return to store |  | PM-A |  |  |  |  | warranty starts | warranty starts | BSRA(end) | [12 empty] | PM e-mail Acounting, no more expenses on project
|  |  |  | 56041 (SC5) Suebpong / Tharawin |  | Design | [6 empty] | Integration of an Ink-Jet unit | Integration of carton data matrix code check with camera Make Cognex | machine to operate cartons with a 4th flap (Hanger flap) |  | B, O, Lp |  |  | W, SO, Fp | SO |  | Fp | SO |  |  |  | list of parts for calibration certificat | FP | Power and Air supply details sheet with location on machine | P |  |  | DQ |  |  |  | SW | WTr=15000Euro - 18% | need to send one more cartrige in ink jet in scope |  | SW | PM to confirm to Ratthana when calibration certificat company to come to IWK | WTr=15000Euro - 18% | PM to confirm to Ratthana when calibration certificat company to come to IWK |  | WTr=15000Euro - 18% | FAT protocol | Fault assistance integrated in machine visualization | DQ customer want to combine for both | WTr=15000Euro - 18%; DQ customer want to combine for both | PM to confirm to Ratthana when calibration certificat company to come to IWK | SAT protocol | IQ,OQ | Noise level measurement with certificate | Pressure gauge calibration certification | Noise level measurement with certificate | Pressure gauge calibration certification | IQ,OQ | Pressure gauge calibration certification | IQ,OQ |  | Pressure gauge calibration certification |  | SAP format marking | Fault Assistance will be prepared after FAT by VPT on CW41
|  |  |  | 56042 (Feeder) Pakiani / Tharawin |  | Design | [10 empty] | 3D | DRi |  | check with Joel about long lead time parts fist unit condom feeder | just ordered on 25.11. (planning) | check with Joel about long lead time parts fist unit condom feeder | FD |  | check with Joel about long lead time parts fist unit condom feeder = will be end of January (3 weeks delay) |  |  |  | FD | DQ | SW (first unit) | SW (first unit) | test (30 min) on 20.2. | test | test | test 30 min | SO |  | WTr=6000Euro - 18% |  |  |  |  | WTr=6000Euro - 18% |  |  | WTr=6000Euro - 18% | FAT protocol | SW | DQ customer want to combine for both | WTr=6000Euro - 18%; DQ customer want to combine for both | PM to confirm to Ratthana when calibration certificat company to come to IWK | SAT protocol | IQ,OQ |  | Pressure gauge calibration certification |  | Pressure gauge calibration certification | IQ,OQ | Pressure gauge calibration certification | IQ,OQ |  | Pressure gauge calibration certification
Operation
|  |  |  | Planned | Setting phase | Q (quality) | [12 empty] | QG3-3 (design to release all on 14.11.) but all released on 25.11. |  | QG3-1(no format confirmation) |  |  | QG3-1(format ocnfirmation, sample just received) | QG3-1(format confirmation delayed to CW2) |  | QG4-3 check with Joel about long lead time parts first unit condom feeder = will be end of January (3 weeks delay); QG3-1 (sample delayed 4 weeks, format drwing just sent and will be confirmed on CW3)\ | QG3-1 |  | QG4-1(basic and option not in house); QG4-3 (basic and option not in house) | QG4-3 | QG5-3 |  |  | QG4-1 | QG3-2 (basic options not released) | QG3-2 (test done earlier, we could move QG3-2 from CW12 to CW11) |  | QG5-1(capacity issue, SW) |  |  |  | QG4-2 basic option not complete); QG5-1 (testing material = carton will receive on CW19 but it's not show stopper; format part pending) | QG5-1 (testine mateial=caron pending) | QG4-2 (basic and option not in house…start weekly meeting) liniar guide x 16 delivery on 17.6. |  |  |  |  | QG5-2 (part delay and testing material expected on CW26) | QG5-2 (testing material coming on 29.6.) | IFd | IFd (F2=F4=F3) | IFd (F2=F4=F3) | IFd(F4) | IFd(F3) | IFd(F1) | FAT (due to customer availability need to move FAT corm CW32 and CW33 to CW34) |  |  |  | FAT (acceptance will be signed after closing LOPs = CW40) |  |  | SAT | I&C | I&C | QG6 | SAT
|  |  |  | Planned |  | C (cost) | [11 empty] | PEC |  | D,M |  |  | 30% | D,M |  |  |  |  | D,M,A,P | 30% |  |  | D,M,A,P | 32% |  | 32% | D,M,A,P |  |  |  |  | D,M,A,P | 32% |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P
|  |  |  | Planned |  | D (Delivery) | [53 empty] | P,L | P,L | ETD |  |  |  | P,L | ETD |  | ETA | [48 empty] | DAP
|  |  |  | Planned |  | Payment | 1046999.5 |  |  | contract | [5 empty] | contract | PO | i30% | [13 empty] | p30% | [25 empty] | i30% |  |  |  | i30% |  |  | i25% | i30% |  |  | i15% | i25% |  |  |  | i15% |  |  | p25% |  | p30% | [6 empty] | p15% | [31 empty] | (credit term 90 days) 30% (DP+Bank Guarntee); 30% (after sucessefull FAT and bank Gurantie); 25% after successful delivery); 15% (after SAT and presentation of a Warranty Guarantee) S/O: 6080056040
| 56000_C_TH_SC5-CondomFeeder Formats: 5 FAT (5 days; 30min) / 5 (5 adjustment charts) I&C by 1 technician for 15 days Execution/Support IQ/OQ by 1 technician for 5 days Training y 1 technician for 3 days |  | B | Adisorn | Setting phase | QG status | 0 | 0 | 45753084 | PO | 30.27% | 36% |  |  |  | QG2 | QG2 |  |  |  | QG3-1 | [12 empty] | FR | QG4-1 |  | QG3-2 | [6 empty] | QG5-1 | QG4-2 | [8 empty] | IFs |  |  |  | QG5-2 | IFs |  | IFd |  | IFd | IFd | IFd | IFd |  | FAT | [7 empty] | QG6 |  |  |  | I&C | I&C | I&C | SAT | Train | [33 empty] | QG3-1 = SC5; QG3-2 = condom feeders
|  |  |  | Patinya / Saksit |  | Milestones | [10 empty] | S,Communication Chanel sheet |  | S,3D inkjet and camera | L | F | F(F1, F2, F4, F5) |  | TM(for first unit) | F(F3) |  |  | F(F3) | F(F3) | F(F3) | final format overview |  |  | clarify all for ordering remaining 3 units +4 +4 = 11 units | IP |  | customer have in stock ready inkjet and camer but we donlt need now they can deliver after songkran | BSRA | receive from customer inkjet and camera; customer want to move instaltion from September to January, IWK to evaluate if FAT shold staty same or we need to move | TM (for 3 formats=F1. F2, F5) |  | receive from customer inkjet and camera | TM (carton) | [5 empty] | WTc | liniar guide x 16 delivery on 17.6. | TM (condom) | IP | [7 empty] | IP |  |  |  |  | IP | BSRA(D) | WTc |  |  |  | pack with machine 3 samples that we run on machine during FAT | summery parts return to store | PM-A
|  |  |  | 56001 (SC5) Suebpong / Tharawin |  | Design | [6 empty] | Integration of an Ink-Jet unit | Integration of carton data matrix code check with camera Make Cognex | machine to operate cartons with a 4th flap (Hanger flap) |  | B, O, Lp | Lp | W | Fp | SO | [7 empty] | FP | P; list of parts for calibration certificat | Power and Air supply details sheet with location on machine |  | Power and Air supply details sheet with location on machine | DQ |  |  |  | SW | WTr=15000Euro - 18% |  |  | SW | PM to confirm to Ratthana when calibration certificat company to come to IWK |  | DQ | WTr=15000Euro - 18% | Fault assistance integrated in machine visualization | FAT protocol |  | Pressure gauge calibration certification |  | SAT protocol | IQ,OQ | [8 empty] | IQ,OQ |  |  |  |  | IQ,OQ |  |  |  |  | SAP format marking
|  |  |  | 56002 (Feeder) Pakiani / Tharawin |  | Design | [11 empty] | DRi |  |  |  |  | FD | [5 empty] | FD | DQ | SW (first unit) | SW (first unit) |  | DQ |  |  | SO |  | WTr=6000Euro - 18% | [5 empty] | DQ | WTr=6000Euro - 18% |  | FAT protocol | SW |  | PM to confirm to Ratthana when calibration certificat company to come to IWK | SAT protocol | IQ,OQ |  |  |  |  | SW |  | PM to confirm to Ratthana when calibration certificat company to come to IWK |  | IQ,OQ |  |  |  |  | IQ,OQ |  |  |  |  | SAP format marking
[6 empty] | Operation | [50 empty] | SO |  | BSR (F1)
|  |  |  | Planned | Setting phase | Q (quality) | [14 empty] | QG3-1(no format confirmation) | [8 empty] | QG4-1 (basic not in house) |  | QG4-1 (only one group - product chain (chain guide) will arrive on CW10) |  |  | QG4-1 | QG3-2 (basic options not released) | QG3-2 (test done earlier, we could move QG3-2 from CW12 to CW11) |  | QG5-1 (on CW13 we moved FAT from CW31 to CW36 due instlation moving from September 2026 to January 2027) |  |  |  | QG4-2 (basic option pending) | QG5-1 | QG4-2 (basic and option not in house…start weekly meeting) liniar guide x 16 delivery on 17.6. |  |  |  |  | QG5-2 (during project status meeting on 28.5. agreed to moved QG5-2 from CW25 to CW27) |  | QG5-2 (production capacity) |  | IFs(product bundery is missing) |  | FAT (on CW13 we moved FAT from CW31 to CW36 due instlation moving from September 2026 to January 2027) | QG5-2 (modify parts not in house; format parts not in house; SW not done; assmebly capacity) | QG5-2 (production capacity) | IFs(some pending parts) | IFd(F2) need to continue on CW37 | FAT (due to new design and production capacity we request to move FAT from CW36 to CW42…as anyway customer request delivery on CW2 / January 2027) | IFd(F2) | IFd(F2; F3;F4) | IFd(F3;F4) | IFd(F5) | IFd(F1) | FAT (due to bublic holiday in CW42 custoer request to move FAT to CW43 | FAT | [7 empty] | QG6
|  |  |  | Planned |  | C (cost) | [11 empty] | PEC |  | D,M |  |  | 31% | D,M |  |  |  |  | D,M,A,P | 31% |  |  | D,M,A,P | 36% |  | 36% | D,M,A,P |  |  |  |  | D,M,A,P | 36% |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P
|  |  |  | Planned |  | D (Delivery) | [53 empty] | P,L |  |  |  |  | P | [7 empty] | P | L,ETA | [43 empty] | door to door
|  |  |  | Planned |  | Payment |  |  | 45753084 | 4503744319 | [5 empty] | contract | PO | i30% | [12 empty] | p30% | [24 empty] | i30% | [6 empty] | i25% |  |  |  | i30% | i15% | [5 empty] | i25% | [5 empty] | p30% |  |  |  | i15% |  |  | p25% | [10 empty] | p15% | [19 empty] | (credit term 90 days) 30% (DP+Bank Guarntee); 30% (after sucessefull FAT and bank Gurantie); 25% after successful delivery); 15% (after SAT and presentation of a Warranty Guarantee)
| 56000_SSL_TH_SC5-CondomFeeder additional format (set of size parts) |  |  | Add-on |  | Delivery (Add on) |  |  | 786708
|  |  |  | Planned |  | Payment (Add on) | [40 empty] | Qto
|  |  |  | Sale / PE |  | Milestones | [6 empty] | Adisorn and Stefanie will check how many we need to setting 2 machine ( we have 13000 tubes) |  |  |  | TM (utilize internal) | [5 empty] | Pre-Assembly Finish - CW50 |  | Final assembly start - CW52 (before Holidays) |  |  |  |  | check with Joel after processing in SAP | [31 empty] | Nut to organzie meeting for setting timeline | [9 empty] | BSRA(D) |  | BSRA(end)
|  |  |  | 56121 Pongsapak / Henoch |  | Design | [10 empty] | P | [19 empty] | SW
|  |  |  | Planned | #REF! | Q (quality) | [10 empty] | QG4(project was not prioritiezed by purchase because is intenal project) |  |  |  | QG4 | [7 empty] | QG3 | QG5(moved to proejct PT Maiyume_ID |  |  |  |  | QG4 (options, and electric parts pending) |  | QG4(option not in house) | QG4 | QG5 (on CW13 agreed to move QG5 to CW21 due to delay parts and capacity) this proejct is note priority | [5 empty] | QG5 moved from CW20 to CW27 due to capacity (not urgent project) |  | IFd | [21 empty] | QG5 |  |  |  | IFd
|  |  |  | Actual |  | C (cost) | [9 empty] | D,M,A,P |  |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P
|  |  |  | Done |  | D (Delivery)
|  |  |  | Planned |  | Payment
| 56090_D_IN_SC5-OEM Formats: 4 FAT (3 days; 10min=F2, F5, F9, F13) / 16 (15 adjust. chart) I&C by 1 technician over 5 weeks |  | B | Chettapong | Setting phase | QG status | 1018768.35 | 0 | 0 | PO | 39% | 40% | [10 empty] | QG1 | QG2 | [7 empty] | QG3,DR | DRi | FR | [12 empty] | QG4 | [13 empty] | QG5 |  |  |  | IFd | IFd | IFd | IFd |  | FAT | [6 empty] | QG6 |  |  |  |  | I&C | I&C | I&C | I&C | SAT | [31 empty] | CW11: DRAFT
|  |  |  | Nihar / Raghu |  | Milestones | [16 empty] | Raghu Sample (need to check with Raghu which samples we received (vial=7 formats, booklet=all sizes, carton= ???sizes); Format overview - Raghu need to calrify with customer; URS - during kick off with customer check to sign, Raghu to prepare diviation list from URS | S | Communication Chanel sheet | S (for Kraus) check how much TM thay need; S (for Linapack) check how much TM thay need | 3D and wiring (Kraus); sugested 4 formats for FAT, customer to confirm | 3D and wiring (Ink-Jet unit; print control camera,Kraus, Linapack) | 3D and wiring ( Linapack) | L | 3D and wiring (Jekson Ink-Jet unit; print control camera) | F | BSRA | final format overview; mock up carton; | 3D and wiring (Jekson Ink-Jet unit; print control camera) | IWK desing will share simulation 11.3. by using Olivier parameter; | FAT criteria (PM+design+production); ; mock up carton; TM(for Kraus 200 booklets per format) | TM (customer will send on 24.3. expect on 27.3. mock up carton; booklet for kraus and vials for linapck) ; WTr 16170 Euro - % = 11480.70 Euro; | TM (only vials 7 sizes for Linapack) | TM(booklet) mock up carton | WTr 16170 Euro - % = 11480.70 Euro; | receive from customer (Ink-Jet unit; print control camera) | TM(booklet for Kraus) mock up carton.; receive Kraus (booklet feeder) | TM(booklet sample, mock up carton=expect on 7.5.); | receive Kraus (booklet feeder); final format overview | test turn table at Linapack | WTr 16170 Euro - % = 11480.70 Euro; | TM | FAT for Linapack (one of 7 vial sizes has biger cap then body) | we absorbed cost of glue around 5500 THB | FAT for Linapack ; receive Linapack; receive from customer (Ink-Jet unit; print control camera) | Linapack one of 7 vial sizes has biger cap then body - customer mentioned that this is miustake from supler all vials shoild have bigger body then cap | IP; TM (customer delay will be dispatch oin 6.7. should arrive within July); receive Linapack; | IP,WTc | receive Linapack . 1st time : around CW34, to support set up machine. we will inform exactly date again. 2nd time : support our FAT around CW40. | TM only vials (customer delay will be dispatch oin 6.7. should arrive within July) | PM to confirm to Ratthana when calibration certificat company to come to IWK | Request Jekson engineer to support set up machine 2 times | PM to confirm to Ratthana when calibration certificat company to come to IWK |  |  | TM (booklet, carton) | Jekson (1st time on CW38 (14-18 Sep) | calibration certificat prepared | Jekson (1st time on CW38 (14-18 Sep) | Jekson 2nd time on CW41 (5-9 Oct) pack with machine 3 samples that we run on machine during FAT |  |  | BSRA(D) | Jekson 2nd time on CW45 (?) pack with machine 3 samples that we run on machine during FAT |  |  |  | summery parts return to store |  | PM-A | [10 empty] | if PO-VPT but instation done by Thailand, after instalation handover to VPT aftersales (PM Thai, PM VPT, Sarit, Alexsandre) | warranty starts (warranty is 12 months or 2000 operation housr, depend on which occure firest. Warranty valid starting after SAT but not latter then 90 days after FAT) | BSRA(end) | PM e-mail Acounting, no more expenses on project (over 400000Euro)
|  |  |  | 56091 Suebpong / Tharawin |  | Design | [15 empty] | Integration of an Ink-Jet unit; Integration of a print control with camera ; Batch report changes will be done by VPT;Machine IPC upgrade with B&R APC4100 for compatibility with RAID system | OEM (Linsapack and Rontech) need sample, testing material, timaline, 3D | B, release Kraus (booklet feeder) | Fp |  | Lp | URS for Linapack |  | PO for Linapack | SO,W,ND(Pusher Arm For Multi Vial insertion to Carton (5*2) in SC5) |  |  |  | FP |  |  | FD(Pusher Arm For Multi Vial insertion to Carton (5*2) in SC5) | back up plan if this solutin for turn table not working; we need to check FAT date with Linapack. We need to check when we can have result form plan A…after we need to check how long we need to exacute plan B | DQ |  |  | FP | Power and Air supply details sheet with location on machine | DQ, list of parts for calibration certificat | P | DQ | Power and Air supply details sheet with location on machine |  |  | SW | [9 empty] | FAT protocol | IQ,OQ | FAT protocol |  | IQ,OQ | [8 empty] | SAP format marking
[6 empty] | Operation | [53 empty] | BSR (F1) | Basic set up + F.2 (Glue) set up | F.2 (Glue) set up continue | F.5 (Glue) set up | F.9 (Tuckin) set up | F.13 (Tuckin) set up + F.11 & F.12 (F.11,F.12 has same carton, vial with F.13 but different only booklet) | IFd(F2) |  |  | non FAT format F12; F1; F11 |  | non FAT format F4; F6; F7 | non FAT format F10; F8; F14 | non FAT format F15; F16
|  |  |  | Planned | Setting phase | Q (quality) | [16 empty] | QG1 (Format overview - Raghu need to calrify with customer; URS - during kick off with customer check to sign, Raghu to prepare diviation list from URS) | QG2 | [6 empty] | QG3 (option not released; format not confirmed) | QG3 | [11 empty] | QG4 (option not in house) |  | QG4 (basic not in house; late add parts) | QG4 (follow product chain boundery on CW23) | [7 empty] | QG5 (assembly not complete, waiting modify parts, big issue gear wheel rotation) |  |  | QG5 (need to wait guarding at overhad change) | QG5 (program not finished, testing material not arrived) | IFd(F5) | QG5(follow up testing material and some modification parts) | IFd(F2) | IFd(F5) | IFd(F9) | IFd(F9) | FAT (testing material arrived on CW37 instead CW23 - but we could wait until CW31) | IFd(F5) | IFd(F13) |  | FAT |  |  |  | I&C | I&C | I&C | I&C | SAT
|  |  |  | Planned |  | C (cost) | [18 empty] | PEC |  |  |  | D | 39% |  |  | D | 40% |  | 40% | D,M |  |  |  |  | D,M | 40% |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  | D,M,A,P
|  |  |  | Planned |  | D (Delivery) | [16 empty] | 10 months FAT from the date of PO (4.12.2025.) | [42 empty] | L.D. Clase: In the event of a delay in delivery for which Supplier is solely responsible & following a grace period of 1.5 weeks, the Purchaser is entitled to claim liquidated damages of 0.5% of the net price of the delayed part of the Equipment per full week of delay, up to a maximum of 5% of the net value of the delayed part of the Equipmen |  |  | P,L | ETD |  |  |  | P,L | ETD |  |  | ETA | [39 empty] | CIF Chennai
|  |  |  | Planned |  | Payment | 1018768.35 |  |  | 4700033881 | [12 empty] | PO;i40% |  | p40% | [40 empty] | i50% |  |  |  | i50% |  |  |  | p50% | [7 empty] | i10% |  |  |  | p10% | [31 empty] | (credit term 30 days) 40% Adv upon order confirmation & submission of Proforma Invoice; 50% Against successful FAT; 10% against I&C and upon submission of PBG Valid for 12 months from the date of I&C or 150 days from Bill of Lading, whichever is earlier. S/O: 6080056090
|  |  |  | Siva (Patinya) |  | Milestones | [6 empty] | Cosmed plans to make the next payment on SEP 30th | [12 empty] | pending payment 278200THB+278200THB+1112800THB | [20 empty] | sending machine to India for exibition; Packing & Loading: 29.05.2026; VESSEL: ZHONG GU TAI YUAN V.2602W; ETD: 07.06.2026; ETA NHAVA SHEVA: 21.06.2026 | VPT send 15000 tubes for Hydrabat |  |  |  | VPT or Thailand send 15000 tubes for Delih | Pharma Pro&Pack Expo 2026 (9th - 11th July) Hyderabad | [9 empty] | Apichat 18.9.26.We agree on the followings: • Winner will provide the details and samples of format parts on next week • We confirm 3-4 months manufacturing time • Winner will settle the final payment before February 2027, and prior to the delivery | [9 empty] | PMEC 2026 (24th - 26th November) Delhi |  |  |  | receive machine back in Thailand
|  |  |  | Natnararat |  | Design
|  |  |  | Planned | #REF! | Q (quality)
|  |  |  | Delay |  | C (cost)
|  |  |  | Delay |  | D (Delivery) | [111 empty] | door to door latest by March (receive at site September, 2021)
|  |  |  | Delay |  | Payment |  |  | 6955000 | 6508004 | [6 empty] | 1112k | [14 empty] | p(278k) |  |  |  | p(278k) |  |  | pending 5 x 278K (last payment received in February 2026) customer committed to pay within this year | p(278k) |  |  |  |  | p(278k) |  |  |  | p(278k) | [15 empty] | 347,750.00 THB. |  |  |  | 347,750.00 THB. |  |  |  | 347,750.00 THB. |  |  |  |  | 347,750.00 THB. | [39 empty] | (credit term 30 days) P1=20%; P2=20%; P3=20%; P4=20%; P5=20%;
| 55733_E_IN_HC5 Formats: FAT (3 days FAT) / 4 (5+1 adjustment chart) I&C by 2 technicians for 25 days SAT by 2 technicians for 5 days |  | C | Chettapong | On hold | Delay | 0 | 0 | 0 | PO | [17 empty] | QG1 | QG2 |  |  |  |  | DR; QG3 | [83 empty] | CW11: DRAFT
|  |  |  | Nihar / Raghu |  | Milestones | [21 empty] | Communication Chanel sheet | S (customer will bring on CW9 during FAT) | 3D(Ink-Jet unit; print control with camera)…decide if they keep inkjet and camera from old project or they will send new one | on hold until FAT of 55670 on CW9 | Test speed of F8 (5th flap) = speet 120 | L,F | S | BSRA | Hemang will inform if PO will be on CW18 or earlier | final format overview | [9 empty] | TM | IP |  |  | PM to confirm to Ratthana when calibration certificat company to come to IWK | [5 empty] | BSRA(D) | pack with machine 3 samples that we run on machine during FAT | summery parts return to store |  | PM-A | warranty starts (warranty is 12 months or 2000 operation housr, depend on which occure firest. Warranty valid starting after SAT but not latter then 90 days after FAT) | BSRA(end) | PM e-mail Acounting, no more expenses on project
|  |  |  | 55733 (HC5) Wimala / Tharawin |  | Design | [19 empty] | Integration of an Ink-Jet unit; Integration of a print control with camera; | conect to 55430_Galentic Pharma_IN_TZ101-FP46-2XL | speed of 5th flap During encube we could run 100-110/min (need to test on HC5 machine Galentic | Lp | Fp |  | SO,W |  | FP |  |  |  |  | DQ |  |  | P | Power and Air supply details sheet with location on machine | list of parts for calibration certificat |  |  | SW |  |  |  |  | FAT protocol |  |  | IQ,OQ | calibration certificat prepared |  |  | SAP format marking
[6 empty] | Operation | [54 empty] | EB | [7 empty] | ECR |  |  |  | SO |  |  | BSR (F1)
|  |  |  | Planned | On hold | Q (quality) | [21 empty] | QG1 (samples not available, no information for sample delivery) | QG2 |  |  | QG3 (we do not release before we get PO…PO expected after FAT of 55670 on CW9) |  | QG3 | FR | [7 empty] | QG4 | [6 empty] | QG5 | IFs |  | IFd | IFd | IFd | IFd |  | FAT |  |  | QG6? |  | SAT?
|  |  |  | Delay |  | C (cost) | [23 empty] | PEC |  |  | D |  |  |  | D,M | [8 empty] | D,M,A,P |  |  |  | D,M,A,P
|  |  |  | Delay |  | D (Delivery) | [20 empty] | FAT 6 month from PO | [32 empty] | P,L | ETD |  |  | ETA | [53 empty] | Ex-works IWK Thailand, i
|  |  |  | Planned |  | Payment | [20 empty] | LOI |  |  |  |  | PO | [10 empty] | PO - with expected FAT in November | i20% |  |  |  | p20% | [9 empty] | i70% |  |  |  | p70% | i10% |  |  | p10% | [51 empty] | (credit term 30 days) 20% (DP); 70% payment by T/T after successful FAT & before shipment of machine; 10% after successful installation and commissioning or 90 days from bill of lading whicheve earlier S/O: 6080055733
| 56090_F_IN_SC5-OEM Formats: 4 FAT (3 days; 10min=F2, F5, F9, F13) / 16 (15 adjust. chart) I&C by 1 technician over 5 weeks |  | B | Chettapong | Setting phase | QG status | 1018768.35 | 0 | 0 | PO | 39% | 40% | [10 empty] | QG1 | QG2 | [7 empty] | QG3,DR | DRi | FR | [12 empty] | QG4 | [13 empty] | QG5 |  |  |  | IFd | IFd | IFd | IFd |  | FAT | [6 empty] | QG6 |  |  |  |  | I&C | I&C | I&C | I&C | SAT | [31 empty] | CW11: DRAFT
|  |  |  | Nihar / Raghu |  | Milestones | [16 empty] | Raghu Sample (need to check with Raghu which samples we received (vial=7 formats, booklet=all sizes, carton= ???sizes); Format overview - Raghu need to calrify with customer; URS - during kick off with customer check to sign, Raghu to prepare diviation list from URS | S | Communication Chanel sheet | S (for Kraus) check how much TM thay need; S (for Linapack) check how much TM thay need | 3D and wiring (Kraus); sugested 4 formats for FAT, customer to confirm | 3D and wiring (Ink-Jet unit; print control camera,Kraus, Linapack) | 3D and wiring ( Linapack) | L | 3D and wiring (Jekson Ink-Jet unit; print control camera) | F | BSRA | final format overview; mock up carton; | 3D and wiring (Jekson Ink-Jet unit; print control camera) | IWK desing will share simulation 11.3. by using Olivier parameter; | FAT criteria (PM+design+production); ; mock up carton; TM(for Kraus 200 booklets per format) | TM (customer will send on 24.3. expect on 27.3. mock up carton; booklet for kraus and vials for linapck) ; WTr 16170 Euro - % = 11480.70 Euro; | TM (only vials 7 sizes for Linapack) | TM(booklet) mock up carton | WTr 16170 Euro - % = 11480.70 Euro; | receive from customer (Ink-Jet unit; print control camera) | TM(booklet for Kraus) mock up carton.; receive Kraus (booklet feeder) | TM(booklet sample, mock up carton=expect on 7.5.); | receive Kraus (booklet feeder); final format overview | test turn table at Linapack | WTr 16170 Euro - % = 11480.70 Euro; | TM | FAT for Linapack (one of 7 vial sizes has biger cap then body) | we absorbed cost of glue around 5500 THB | FAT for Linapack ; receive Linapack; receive from customer (Ink-Jet unit; print control camera) | Linapack one of 7 vial sizes has biger cap then body - customer mentioned that this is miustake from supler all vials shoild have bigger body then cap | IP; TM (customer delay will be dispatch oin 6.7. should arrive within July); receive Linapack; | IP,WTc | receive Linapack . 1st time : around CW34, to support set up machine. we will inform exactly date again. 2nd time : support our FAT around CW40. | TM only vials (customer delay will be dispatch oin 6.7. should arrive within July) | PM to confirm to Ratthana when calibration certificat company to come to IWK | Request Jekson engineer to support set up machine 2 times | PM to confirm to Ratthana when calibration certificat company to come to IWK |  |  | TM (booklet, carton) | Jekson (1st time on CW38 (14-18 Sep) | calibration certificat prepared | Jekson (1st time on CW38 (14-18 Sep) | Jekson 2nd time on CW41 (5-9 Oct) pack with machine 3 samples that we run on machine during FAT |  |  | BSRA(D) | Jekson 2nd time on CW45 (?) pack with machine 3 samples that we run on machine during FAT |  |  |  | summery parts return to store |  | PM-A | [10 empty] | if PO-VPT but instation done by Thailand, after instalation handover to VPT aftersales (PM Thai, PM VPT, Sarit, Alexsandre) | warranty starts (warranty is 12 months or 2000 operation housr, depend on which occure firest. Warranty valid starting after SAT but not latter then 90 days after FAT) | BSRA(end) | PM e-mail Acounting, no more expenses on project (over 400000Euro)
|  |  |  | 56091 Suebpong / Tharawin |  | Design | [15 empty] | Integration of an Ink-Jet unit; Integration of a print control with camera ; Batch report changes will be done by VPT;Machine IPC upgrade with B&R APC4100 for compatibility with RAID system | OEM (Linsapack and Rontech) need sample, testing material, timaline, 3D | B, release Kraus (booklet feeder) | Fp |  | Lp | URS for Linapack |  | PO for Linapack | SO,W,ND(Pusher Arm For Multi Vial insertion to Carton (5*2) in SC5) |  |  |  | FP |  |  | FD(Pusher Arm For Multi Vial insertion to Carton (5*2) in SC5) | back up plan if this solutin for turn table not working; we need to check FAT date with Linapack. We need to check when we can have result form plan A…after we need to check how long we need to exacute plan B | DQ |  |  | FP | Power and Air supply details sheet with location on machine | DQ, list of parts for calibration certificat | P | DQ | Power and Air supply details sheet with location on machine |  |  | SW | [9 empty] | FAT protocol | IQ,OQ | FAT protocol |  | IQ,OQ | [8 empty] | SAP format marking
[6 empty] | Operation | [53 empty] | BSR (F1) | Basic set up + F.2 (Glue) set up | F.2 (Glue) set up continue | F.5 (Glue) set up | F.9 (Tuckin) set up | F.13 (Tuckin) set up + F.11 & F.12 (F.11,F.12 has same carton, vial with F.13 but different only booklet) | IFd(F2) |  |  | non FAT format F12; F1; F11 |  | non FAT format F4; F6; F7 | non FAT format F10; F8; F14 | non FAT format F15; F16
|  |  |  | Planned | Setting phase | Q (quality) | [16 empty] | QG1 (Format overview - Raghu need to calrify with customer; URS - during kick off with customer check to sign, Raghu to prepare diviation list from URS) | QG2 | [6 empty] | QG3 (option not released; format not confirmed) | QG3 | [11 empty] | QG4 (option not in house) |  | QG4 (basic not in house; late add parts) | QG4 (follow product chain boundery on CW23) | [7 empty] | QG5 (assembly not complete, waiting modify parts, big issue gear wheel rotation) |  |  | QG5 (need to wait guarding at overhad change) | QG5 (program not finished, testing material not arrived) | IFd(F5) | QG5(follow up testing material and some modification parts) | IFd(F2) | IFd(F5) | IFd(F9) | IFd(F9) | FAT (testing material arrived on CW37 instead CW23 - but we could wait until CW31) | IFd(F5) | IFd(F13) |  | FAT |  |  |  | I&C | I&C | I&C | I&C | SAT
|  |  |  | Planned |  | C (cost) | [18 empty] | PEC |  |  |  | D | 39% |  |  | D | 40% |  | 40% | D,M |  |  |  |  | D,M | 40% |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  | D,M,A,P
|  |  |  | Planned |  | D (Delivery) | [16 empty] | 10 months FAT from the date of PO (4.12.2025.) | [42 empty] | L.D. Clase: In the event of a delay in delivery for which Supplier is solely responsible & following a grace period of 1.5 weeks, the Purchaser is entitled to claim liquidated damages of 0.5% of the net price of the delayed part of the Equipment per full week of delay, up to a maximum of 5% of the net value of the delayed part of the Equipmen |  |  | P,L | ETD |  |  |  | P,L | ETD |  |  | ETA | [39 empty] | CIF Chennai
|  |  |  | Planned |  | Payment | 1018768.35 |  |  | 4700033881 | [12 empty] | PO;i40% |  | p40% | [40 empty] | i50% |  |  |  | i50% |  |  |  | p50% | [7 empty] | i10% |  |  |  | p10% | [31 empty] | (credit term 30 days) 40% Adv upon order confirmation & submission of Proforma Invoice; 50% Against successful FAT; 10% against I&C and upon submission of PBG Valid for 12 months from the date of I&C or 150 days from Bill of Lading, whichever is earlier. S/O: 6080056090
|  |  |  | Siva (Patinya) |  | Milestones | [6 empty] | Cosmed plans to make the next payment on SEP 30th | [12 empty] | pending payment 278200THB+278200THB+1112800THB | [20 empty] | sending machine to India for exibition; Packing & Loading: 29.05.2026; VESSEL: ZHONG GU TAI YUAN V.2602W; ETD: 07.06.2026; ETA NHAVA SHEVA: 21.06.2026 | VPT send 15000 tubes for Hydrabat |  |  |  | VPT or Thailand send 15000 tubes for Delih | Pharma Pro&Pack Expo 2026 (9th - 11th July) Hyderabad | [9 empty] | Apichat 18.9.26.We agree on the followings: • Winner will provide the details and samples of format parts on next week • We confirm 3-4 months manufacturing time • Winner will settle the final payment before February 2027, and prior to the delivery | [9 empty] | PMEC 2026 (24th - 26th November) Delhi |  |  |  | receive machine back in Thailand
|  |  |  | Natnararat |  | Design
|  |  |  | Planned | #REF! | Q (quality)
|  |  |  | Delay |  | C (cost)
|  |  |  | Delay |  | D (Delivery) | [111 empty] | door to door latest by March (receive at site September, 2021)
|  |  |  | Delay |  | Payment |  |  | 6955000 | 6508004 | [6 empty] | 1112k | [14 empty] | p(278k) |  |  |  | p(278k) |  |  | pending 5 x 278K (last payment received in February 2026) customer committed to pay within this year | p(278k) |  |  |  |  | p(278k) |  |  |  | p(278k) | [15 empty] | 347,750.00 THB. |  |  |  | 347,750.00 THB. |  |  |  | 347,750.00 THB. |  |  |  |  | 347,750.00 THB. | [39 empty] | (credit term 30 days) P1=20%; P2=20%; P3=20%; P4=20%; P5=20%;
| 55733_G_IN_HC5 Formats: FAT (3 days FAT) / 4 (5+1 adjustment chart) I&C by 2 technicians for 25 days SAT by 2 technicians for 5 days |  | C | Chettapong | On hold | Delay | 0 | 0 | 0 | PO | [17 empty] | QG1 | QG2 |  |  |  |  | DR; QG3 | [83 empty] | CW11: DRAFT
|  |  |  | Nihar / Raghu |  | Milestones | [21 empty] | Communication Chanel sheet | S (customer will bring on CW9 during FAT) | 3D(Ink-Jet unit; print control with camera)…decide if they keep inkjet and camera from old project or they will send new one | on hold until FAT of 55670 on CW9 | Test speed of F8 (5th flap) = speet 120 | L,F | S | BSRA | Hemang will inform if PO will be on CW18 or earlier | final format overview | [9 empty] | TM | IP |  |  | PM to confirm to Ratthana when calibration certificat company to come to IWK | [5 empty] | BSRA(D) | pack with machine 3 samples that we run on machine during FAT | summery parts return to store |  | PM-A | warranty starts (warranty is 12 months or 2000 operation housr, depend on which occure firest. Warranty valid starting after SAT but not latter then 90 days after FAT) | BSRA(end) | PM e-mail Acounting, no more expenses on project
|  |  |  | 55733 (HC5) Wimala / Tharawin |  | Design | [19 empty] | Integration of an Ink-Jet unit; Integration of a print control with camera; | conect to 55430_Galentic Pharma_IN_TZ101-FP46-2XL | speed of 5th flap During encube we could run 100-110/min (need to test on HC5 machine Galentic | Lp | Fp |  | SO,W |  | FP |  |  |  |  | DQ |  |  | P | Power and Air supply details sheet with location on machine | list of parts for calibration certificat |  |  | SW |  |  |  |  | FAT protocol |  |  | IQ,OQ | calibration certificat prepared |  |  | SAP format marking
[6 empty] | Operation | [54 empty] | EB | [7 empty] | ECR |  |  |  | SO |  |  | BSR (F1)
|  |  |  | Planned | On hold | Q (quality) | [21 empty] | QG1 (samples not available, no information for sample delivery) | QG2 |  |  | QG3 (we do not release before we get PO…PO expected after FAT of 55670 on CW9) |  | QG3 | FR | [7 empty] | QG4 | [6 empty] | QG5 | IFs |  | IFd | IFd | IFd | IFd |  | FAT |  |  | QG6? |  | SAT?
|  |  |  | Delay |  | C (cost) | [23 empty] | PEC |  |  | D |  |  |  | D,M | [8 empty] | D,M,A,P |  |  |  | D,M,A,P
|  |  |  | Delay |  | D (Delivery) | [20 empty] | FAT 6 month from PO | [32 empty] | P,L | ETD |  |  | ETA | [53 empty] | Ex-works IWK Thailand, i
|  |  |  | Planned |  | Payment | [20 empty] | LOI |  |  |  |  | PO | [10 empty] | PO - with expected FAT in November | i20% |  |  |  | p20% | [9 empty] | i70% |  |  |  | p70% | i10% |  |  | p10% | [51 empty] | (credit term 30 days) 20% (DP); 70% payment by T/T after successful FAT & before shipment of machine; 10% after successful installation and commissioning or 90 days from bill of lading whicheve earlier S/O: 6080055733
POP Projects (proof of principle)
| 56300_F_TH-FP10 Rockwell PLC (POP) plastic tube |  |  | Mladen | Purchase phase | QG status | [41 empty] | QG1&2 |  |  |  |  | IDR |  | QG3 (to follow wiring and design for HIM panel) | [10 empty] | QG4 | [7 empty] | QG5 |  | IFd
|  |  |  | Tunyatorn |  | Milestones | [40 empty] | development for this is only Design & Programming, everything else will be handled with the Machine Project. | Operator panel Make Allen-Bradley; Control system Make Rockwell, Model Controllogix; Additional Allen-Bradley servo x 5 sets | B | B | "Witawas Metapakwatpan" <wmetapa@ra.rockwell.com> SW from Rokvel | W | NDA to sign with Joel ( not information to be exposed) | SO, Major issue is wiring diagram --> it is a special project then it is important task. | F(plastic tube); | W | Witawas start meetings every 2 weeks |  |  |  | 3D model for Rokwell (removing every measurement(just to keep moving part, sensors, tube holder...) | [5 empty] | SW (Witawas) | Pre-assembly Mechanical + E-Cabinet can begin but target completed |  | comitioining with Vitavas | Final assembly Target
|  |  |  | Jetsadapat / Henoch |  | Design | [41 empty] | no need to order format parts, chiller, | [8 empty] | EB
|  |  |  | Planned | Purchase phase | Q (quality) | [45 empty] | IDR |  | QG3 | [7 empty] | QG4 (Rokwel parts delayed to January but should be earlier, goal by end of Septamber) | [7 empty] | QG5 |  |  |  |  | IFd
|  |  |  | Sale / PE |  | Milestones | [59 empty] | traiding goods(sample , lead time, testing mateiral, 3D) | delivery shifting? | e-mail / VPT aftersales support | format range checked (owner, anuwat, Prasert, PM) | S | Communication Chanel sheet | if punching tool need to request about 500 tubes for test | D | S(for OEM) | L | F,new BSRA | request 50 tubes of metal tubes for test tube holder | WTr (For customers under VPT territory and US territory, the final pricing must follow the respective VPT pricing structure) From provided list until receiving price 1 week (small listing) to 3 weeks (large listing). | final format overview | product spec | pump spec | 3D(from OEM) | WTc | B | TM(for OEM) | TM | IP |  |  |  |  | For every machine, when the customer order Fault Assistance will be prepared after FAT | BSRA(D) |  | TZF (hopper down, 20' container) | pack with machine 3 samples that we run on machine during FAT | summery parts return to store | PM-A |  | if PO-VPT but instation done by Thailand, after instalation handover to VPT aftersales (PM Thai, PM VPT, Sarit, Alexsandre) | warranty starts (warranty is 12 months or 2000 operation hours, depend on which occur first. Warranty valid starting after SAT but not latter then 90 days after FAT) | BSRA(end) | PM e-mail Acounting, no more expenses on project
|  |  |  | Designer / Programmer |  | Design | [62 empty] | ND, DT we will prepare? | B | Lp | Fp | O | ND | SO,W | FP(if tube holders, need to set releaseing first set of tube holders, and all tube holers) | W | DQ (if no new development DQ can be 4 weeks after QG3; if yes new development DQ can be 3 weeks after function description of new development) | FD | if we have ink-jet need to order one more cartrige to be shipped with machine | FP(all tube holers) | list of parts for calibration certificat | Power and Air supply details sheet with location on machine | P |  |  | SW | PM to confirm to Ratthana when calibration certificat company to come to IWK |  |  |  | FAT protocol | calibration certificat prepared | need to send one more cartrige if ink jet in scope (expire date is matching installation plan) | IQ,OQ |  | SAP format marking
[6 empty] | Operation | [71 empty] | EB | [6 empty] | ECR | PAC | FAC | SO |  | BSR (F1) | Set F2? | Set F3
|  |  |  | Planned |  | Q (quality) | [62 empty] | QG1? | QG2? | [5 empty] | QG3? | [7 empty] | QG4? |  |  |  | QG5? |  |  |  |  | IFd | FAT? |  |  |  | QG6? |  |  |  | SAT?
|  |  |  | Planned |  | C (cost) | [64 empty] | PEC | D |  |  |  |  | D,M |  |  |  | D,M |  |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  |  | D,M,A,P |  |  |  | D,M,A,P |  |  |  | D,M,A,P
|  |  |  | Planned |  | D (Delivery) | [90 empty] | P,L | ETD |  |  |  |  | ETA
|  |  |  | Planned |  | Payment | [61 empty] | PO | BG | i30% | LD clause |  | LC | [19 empty] | LC (in FAT acceptance) | [24 empty] | qw
|  |  |  | Add-on |  | Delivery (Add on)
|  |  |  | Planned |  | Payment (Add on)
[13 empty] | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
[13 empty] | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September
[13 empty] | Calendar year 2025 | [12 empty] | Calendar year 2026 | [12 empty] | Calendar year 2026 | [12 empty] | Calendar year 2026 | [13 empty] | Calendar year 2026 | [12 empty] | Calendar year 2027 | [12 empty] | Calendar year 2027 | [12 empty] | Calendar year 2027
[7 empty] | 7365947.2 | 0 | 106202876 | 37.16
[7 empty] | 10223936.3281 |  |  | 0.938
| History: |  |  | Planned
| QG STATUS: |  |  | Actual
| QG = Quality Gate |  |  | Delay
| DR = Design Review |  |  | Done
IDR= internal design review
FR = Format Review
IFs = Internal FAT static
IFd = Internal FAT dynamic
FAT(TG) = Internal FAT Thai-German
FAT(TU) = Internal FAT Thai-US
FAT = Factory acceptance test
I&C = Instalttion and comitioning
SAT = Site acceptance test
MILESTONES:
S = Samples
L = Layout confirmation
F = Format confirmation
TM = Testing Material
B = Bulk
D = Embosing Digits
IP = IP adresses
WTr = Wear&Tear recommend
WTc = Wear&Tear confirmation
PM-A = PM handover to Aftersales
BSRA = Build Safety Risk Assessment
DESIGN:
Lp= Layout prepared
Fp = format drawings prepared
B = basic machine BOM
O = Option Design
SO = Special Option Design (6 digit in OC)
ND = new development
FD = function desctiption
FP = Format Parts Design
P = Pneumatic diagram
W = wiring
SW = software
DT = Digital Twin
OPERATION:
EB = Electrical BOM complete
BPA = Pre-Assembly start
PAC = Pre-Assembly Complete
ECR = E-Cabinet Ready
FAC = Final Assembly Complete
SO = Switch ON
BSR=Basic Setup Ready (including IO check)
Q (quality):
QG = Quality Gate on time / not passed with reason
FAT = Factory acceptance test on time / not passed
IQ = Installation Qualification
OQ = Operation Qualification
C (cost):
PEC = Project Effort Control
D = desing under project budger
D = desing above project budget
M = material under project budger
M = material above project budget
A = assambly under project budger
A = assambly above project budget
P = programming under project budger
P = programming above project budget
D (delivery):
P = Packing
L = Loading
ETD = estimate time delivery
ETA = estimate time arrival
PAYMENT:
PO = purchase order
i% = Invoice
p% = Payment
BG = Bank Guarantee
LC = Letter of Credit
| 6 | 2400 |  | 14400
| 5 | 2400 |  | 12000
| 4 | 2400 |  | 9600
| 3 | 2400 |  | 7200
| 2 | 2400 |  | 4800
| 1 | 2400 |  | 2400
50400