## QG_Status
QG Documentation Delivery Plan
No. | Project no. | Project Name | PM | Who? | [5 empty] | QG4 DUE (CW) | [8 empty] | IFD DUE (CW) |  |  |  |  | FINAL DUE (CW) | [5 empty] | Documents Done | Documents Required | Progress | Overall Status | Remark
[5 empty] | QG4 | QG5 | IFD | FAT | PL | QG4 | Cert. List | Cert. Mat. | FAT protocol | Cal. list | Adj. (Blak FORM) | ETK (BOM) draft | OEM Draft | Manual draft | IFD | Cal. cert | Cert, Mat | Adj Draft | Manual draft | PL | ETK | OEM | Cert, Mat | Adj | Manual
| 56060 | A_SI_VI5X | Stefanie | pp | CW15 | CW25 | CW27 | CW32 | CW37 |  | N/A | N/A | N/A | N/A | 1 | 1 | 1 | 1 |  | N/A |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | Shipment Done
| 56042 | B CN SC5-CondomFeeder | Karan | NN | CW6 | CW7 | CW27 | CW37 | CW41 |  | N/A | N/A | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1 |  |  |  |  | 0 | 0 |  |  |  |  | FAT Done
| 55735 | C_TH_SC5 | Chettapong | NN | CW18 | CW25 | CW26 | CW7 | CW35 |  | N/A | N/A | N/A | N/A | 1 | 1 | 1 | 1 |  | N/A |  | 1 | 1 |  |  |  |  | 0 | 0 |  |  |  |  | Wait FAT
| 56090 | D IN SC5-OEM | Chettapong | NN | CW22 | CW36 | CW40 | CW45 | CW46 |  | N/A | N/A | 1 | 1 | 1 | 1 | 1 | 0 |  | 1 |  | 1 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | on process
| 56000 | E TH SC5-CondomFeeder_TH | Adisorn | NN | CW10 | CW19 | CW29 | CW43 | CW49 |  | N/A | N/A | 1 | 1 | 1 | 1 | 0 | 0 |  | 1 |  | 0 | 0 |  |  |  |  | 0 | 0
| 56090 | F_IN_SC5-OEM | Chettapong |  | CW22 | CW36 | CW40 | CW45 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  |  |  |  | N/A | N/A |  |  |  |  | Added from Delivery Overview
| 55733 | G_IN_HC5 | Chettapong |  | CW18 | CW25 | CW26 | CW7 | CW35 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  |  |  |  | N/A | N/A |  |  |  |  | Added from Delivery Overview
| 56300 | F_TH-FP10 Rockwell PLC (POP) | Mladen |  | CW41 | CW49 | CW51 | CW17 | CW20 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  |  |  |  | N/A | N/A |  |  |  |  | Added from Delivery Overview
| 56040 | B_CN_SC5-CondomFeeder | Karan |  | CW6 | CW7 | CW27 | CW37 | CW41 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  |  |  |  | N/A | N/A |  |  |  |  | Added from Delivery Overview